## Timeline
Program Planner Spreadsheet
created by Sandy Johnson, sandyj@ksu.edu, 785-462-6281
By entering your program date below you can set target dates for completing promotional materials for your event
Cells in blue can be changed
| Program Name: | Livestock PFT Meeting |  | 2014231
| Date : | 2014-08-19
Promotional materials
| Item | Days prior to event | Completion Target Date
| Brochure | 60 | 2014-06-20
| Poster | 60 | 2014-06-20
| Web listing | 60 | 2014-06-20
| materials to agents | 60 | 2014-06-20
| 1st News release | 45 | 2014-07-05
| 2nd News release | 20 | 2014-07-30
| Radio | 10 | 2014-08-09
| head count to caterer | 7 | 2014-08-12
| other | 5 | 2014-08-14
tradeshow letters
early registration deadline
Formulas:
Completion Target Date = DATE(YEAR(C8), MONTH(C8),DAY(C8)-[Days prior to event])

## Promotion content checklist
Check list of details to include in promotion
Program | Livestock PFT Meeting
Item | News release | brochure | flyer | web
Date
Start time
Location
City, State
Address
Building
Contact for more info
Registration cost
Early registration deadline
Checks payable to:
Mail checks to
Sponsors
Program speakers/topics

## Meeting Checklist
Meeting Checklist
Adapted from a list developed by Robin Reid and the River Valley District
Program Name
Double-check building reservation and how to get key
Double-check with catering and give final head count
Double-check with speakers on timeline and directions to meeting site
Screen
Projectors
Computer
Table for projector
Extension Cord(s)
Microphone/sound system
KSRE Signs for door or exterior of building to note meeting location
Handouts of presentations
Handouts of supporting materials
Flyers/promotion for other upcoming events
Sign-up sheet to collect e-mail and addresses
Set up evaluation
Bring evaluation
KSRE pens or other branded material
KSRE tablecloth
Cash box and start up money
Name tags